## Sheet1
Task Estimates					Notes : 1. Don't adjust the variance and the estimate to get the working estimate to what you think. This work estimate is designed to give some lee way for a slip,it is a risk controlling calculation.

Total Team Utilization				496.00%
Total Effort Estimate				28.4
Total Duration (days)				51.44

Sub Teams / resources	Number of staff	Total Working Days/ Week	Total Utilization
CRM	1	5	80.00%
Java	3	13	208.00%
FLEX	2	8	128.00%
QA	2	5	80.00%
			0.00%
			0.00%
			0.00%
			0.00%

Task name	Story Reference	Owner	Allocation to task	Dependencies	Ideal Day Estimate (man days)	Utilization	Confi-Variance(%)	Estimate From (man days)	Estimate To (man days)	Working Estimate	Why is your confidence not 80% or Over	Realistic Day
	name of the use this is related to	Team member prposed for task	People allocated to the task.	What does the task deliver	Number of days task will take if you work on it full time.	effectiveness on tasks	(100% if there is no doubt the estimate is correct, 0% estimate could be doubled or halfed )	Calculated lower range of your effort estimate.	Calculated upper range of your effort estimate	This is a mid point of the estimate rangeso the most expected estimate	Brief outline of the reason you are not confident.	Calcualted duration based on utilization level on the project
Define API	1412	CRM	1.00		3	80.0%	80.00%	2.4	3.6	3.3		4.13
Develop backend	1414	CRM	1.00		4	80.0%	30.00%	1.2	6.8	5.4		6.75
Define API	1412	CRM	1.00		3	80.0%	80.00%	2.4	3.6	3.3		4.13
Develop backend	1414	CRM	1.00		4	80.0%	80.00%	3.2	4.8	4.4		5.50
Interface to CRM	1412	Java	2.00	Dependent on CRM API definition	3	160.0%	80.00%	2.4	3.6	3.3		2.06
Define API for UI.	1412	Java	1.00		2	80.0%	80.00%	1.6	2.4	2.2		2.75
Develop interface to CRM / FLEX	1412	Java	1.00		2	80.0%	80.00%	1.6	2.4	2.2		2.75
Develop UI	1412	FLEX	1.00	Dependent on Java API definition	5	80.0%	80.00%	4	6	5.5		6.88
Review with product owner	1412	FLEX	1.00		5	80.0%	80.00%	4	6	5.5		6.88
Develop story tests	1412	QA	1.00		2	80.0%	80.00%	1.6	2.4	2.2		2.75
Test story	1412	QA	1.00		5	80.0%	80.00%	4	6	5.5		6.88
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00
				0		100.00%	0	0	0		0.00